Addendum Number 001

Date: 10/09/2025

Project: Climate Adaptation Planning Project

Owner: Trinidad Rancheria

This addendum provides changes and/or clarifications, to the Contract Documents. These modifications pertain to the sections referenced below and to all other referenced or applicable sections in the Contract Documents.

Please sign the addendum receipt acknowledgment form and return to the Owner with your proposal and other required forms and documents.

Changes and/or clarifications to the bidding and contracting documents are as follows:

Changes to RFP Tenative Schedule of Events

- Finalist Selection Date: moved from October 23, 2025 to October 30, 2025.

- Finalist Presentations: moved from October 30, 2025 to November 10, 2025.

  - Specific presentation times will be determined after finalists are selected.

Questions Pertaining to the Request for Proposal:

- Can we get a copy of the presentation?

A copy of the presentation, the meeting recording, and an updated RFP (v2) was sent to all registered Pre-Bid Meeting attendees on 9/24/2025.

- Is it possible to share the list of meeting attendees? AND Would it be possible for Trinidad Rancheria to share the list of attendees from the pre-bid session?

The list of all Pre-Bid Meeting attendees was sent out to all attendees on 10/02/2025 and is included again in Appendix 1 of this document.

- Are you coordinating your climate planning efforts with the other tribes that are part of the marine stewardship area?

At this time, coordination with other tribes that are part of the Yurok–Tolowa Dee-Ni’ Indigenous Marine Stewardship Area has not been planned as part of this effort. However, future opportunities for collaboration may be explored as this project develops.

- Is there flexibility within the deliverable schedule to respond to community needs or unforeseen issues?

Yes, there may be flexibility on a case-by-case basis within the deliverable schedule to respond to community needs or unforeseen issues, provided that all deliverables are completed by July 1, 2027. However, because Steering Team Meetings involve multiple participants, changes to meeting dates may be difficult—or in some cases, not feasible—depending on the timing of the request.

- You mentioned youth outreach, are you also looking for a senior group that you already engage? Just getting a better sense of the different groups that will be engaged. If there are already have established groups or if that is something that the consultant will be expected to participate in? for the outreach, is it all in person or a mix of virtual outreach?

There are no currently active youth or elder groups to engage separately. Engagement with these groups may include community events, activities at the local school, or home visits with Tribal Members as appropriate.

Currently established groups include the Community Working Group (five Tribal members working with the Environmental Department), the Tribal Council (elected leadership), and the Community Council (all Tribal members).

Clarification for Task 2.2 – Stakeholder Engagement

Trinidad Rancheria staff and interns will be primarily responsible for organizing and hosting stakeholder workshops and meetings. These activities are expected to occur primarily in person.

The Consultant’s role is to help design and support the engagement process by:

  - Developing the engagement strategy and approach in collaboration with Trinidad Rancheria staff;

  - Creating or providing materials and tools to support workshops and outreach (such as presentations, handouts, or surveys);

  - Recommending methods and techniques for inclusive and effective engagement; and

  - Documenting engagement activities, feedback, and outcomes for use in subsequent project deliverables.

The Consultant may elect to (but is not required to) attend engagement events as useful to provide technical guidance, answer questions, and ensure engagement results are accurately captured to inform Tasks 3 and 4.

### Clarification for Task 4.6 – Community Outreach on Draft Climate Adaptation Plan

For community outreach on the Draft Climate Adaptation Plan, the Consultant will work with Tribal staff to conduct outreach and gather feedback prior to Steering Team approval.

At a minimum, this will include the following presentations from the Consultant:

- One Tribal Council presentation (leadership), and

- One Community Council presentation (all-ages audience).

Proposals that include either in-person or virtual presentations that feasibly meet project goals will be considered.

- On the map there are multiple areas of interest. Will there be opportunities for the consultants to visit on site after consultants are selected?

This question was addressed during the Pre-Bid Meeting. As stated by Selena Rowan, yes, site visits are preferred and encouraged and there will be opportunities for consultants to visit areas of interest after selection.

- For Project Steering Team meetings 2-8, does Trinidad Rancheria have a specified preference for in-person consultant attendance given the hybrid/virtual format? Is virtual attendance for all 7 of those meetings sufficient?

We do not hold a preference for in-person versus virtual attendance for consultants at the specified meetings at this time.

Questions 8-10: Budget Guidance

- I would like to inquire about the anticipated budget range for this project. Having this information would help us tailor our approach and deliverables to align with your financial expectations while ensuring we can provide the highest quality services.

- What is the not to exceed amount for this project?

- Can Trinidad Rancheria provide more budget detail? Considering the $250,000 grant from BIA, what portion should we estimate will be used for consultant support on this project?

Trinidad Rancheria will not be disclosing budget details for this solicitation. Proposers should develop a scope of work and cost proposal that reflects the described project requirements and their recommended approach.

Questions 11-12: Guidance on Funding Source and Constraints

- What are the constraints on the BIA grant funding? For example, are participant stipends and paying for meeting refreshments allowable?

- Should travel be listed as a separate line item?

BIA budget constraints include but are not limited to the federal cost principles established under the Department of the Interior.

The FY 2023 BIA Tribal Climate Resilience Program RFP, which funded this project, is available at https://www.bia.gov/sites/default/files/dup/inline-files/rfp_fy23_tribal_climate_resilience.pdf  and provides guidance on allowable and disallowed costs.

The Trinidad Rancheria Natural Resources Department may have separate funding available for engagement incentives; therefore, consultants should not include stipends or similar costs in their proposed budgets.

All travel should be listed as a separate line item and must comply with applicable federal grant travel requirements and cost principles, including federal per diem and mileage rates.

APPENDIX 1:

Trinidad Rancheria Natural Resources Department

Pre-Bid Meeting Attendee List

Project: Trinidad Rancheria Climate Adaptation Planning Project

Date of Meeting: 09/22/2025

Location: Virtual Meeting

Host: Selena Rowan, Climate Resiliency Program Manager – srowan@trinidadrancheria.com

| Name | Organization | Email |
| --- | --- | --- |
| Abby Hall | CDR Associates | ahall@cdrassociates.org |
| Alan Nazzaro | Rural Community Assistance Corporation | alan.nazzaro@rcac.org |
| Andrew Nguyen | ARUP | andrew.nguyen@arup.com |
| Brett Vivyan | GHD Inc. | brett.vivyan@ghd.com |
| Bri Goodwin | Strategic Earth Consulting | bri@strategicearth.com |
| Jaimlyn Sypniewski | Two Bears Environmental Consulting, LLC | Jaimlyn@tbec.org |
| Janeen Gordon | Blue Stone Strategy Partners | jgordon@bluestonestrategy.com |
| Jennifer Shasserre | DUDEK | jshasserre@dudek.com |
| Katy Bear Nalven | Sea & Shore Solutions | Katy@sea-shoresolutions.com |
| Katie Lizza | Sea & Shore Solutions | katie@sea-shoresolutions.com |
| Margo Carroll | Two Bears Environmental Consulting, LLC | margo@tbec.org |
| Annje Dodd, Praj White, Lia Nelson, Amelia Vergel de Dios | North Point Consulting Group, Inc. | Annje@northpointeureka.com |
| Poonam Boparai | Ascent Environmental, Inc. | poonam.boparai@ascent.inc |
| Ruthie Maloney | RAM Consulting Services | ruthiemaloney@gmail.com |
| Stefanie Krantz | Picea Consulting Group | Stefanie@picea.group; |
| Windley Knowlton | Cascadia Consulting Group | windley@cascadiaconsulting.com |

Addendum Receipt Acknowledgement Form

Receipt of Acknowledgement:

My firm received Addendum No. 001, consisting of 5 pages, for the Trinidad Rancheria Climate Adaptation Planning Project on _______, 20___

Name of Firm _______________________________________________________________

Name (Print)_________________________________________________________________

Name (Signature)______________________________________________________________

Date: ________________________________________________________________________